## Executive Summary
PMS Integration Roadmap — IN-Gauge
Month-End Report • As of February 18, 2026
Active Integrations — Status at a Glance
PMS Vendor | Product | Phase | Status | Risk | Live Props | Pipeline Props | Est. Pipeline ARR ($K) | Expected Close | Next Action | Technical Go-Live (days)
Opera OnPrem | Opera OnPrem | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 21
Opera Cloud | OHIP API | Production Ready | Complete | Medium | — | — |  | Jun 30, 2026 | Assign v2 migration Owner; define cutover plan & timeline this quarter. | 30
FSPMS | FSPMS PMS | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 18
Lightspeed | Lightspeed PMS | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 14
FOSSE | FOSSE PMS | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 14
OnQ | OnQ PMS | Production Ready | Complete | Medium | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 28
Hyatt EDW | Hyatt EDW | Production Ready | Complete | High | — | — |  | Completed | PGP key rotation due Mar 31 — coordinate with Hyatt IT immediately | 28
InforHMS | Infor HMS | Certified | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 21
Springer Miller | SMS | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 14
Iberostar EDW | Iberostar EDW | Certified | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 18
Prestige | Prestige PMS | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 21
StayNTouch | StayNTouch PMS | Certified | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 14
EMMA TSA | TSA Extract | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 18
Protel | Protel PMS | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 21
HotelKey | HotelKey API | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 28
Cambridge TSA | TSA Extract | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 18
NewHotel | NewHotel API | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 14
TMS | TMS API | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 18
RoomMaster | RoomMaster API | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 14
VHP | VHP PMS | Production Ready | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 14
Shiji SEP | Shiji SEP API | Certified | Complete | Medium | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 21
MEWS | MEWS API | Certified | Complete | Low | — | — |  | Completed | No Further Action - In Production & Ready for Onboarding | 21
Cloudbeds | Cloudbeds API | Discovery | On Deck | Medium | — | — |  | 2026-06-30 | Feb 24 - Pulled from Backlog - No current Action | —
Hostaway | Hostaway API | Discovery | On Deck | Medium | — | — |  | Jul 31, 2026 | Feb 24 - Pulled from Backlog - No current Action | —
Roomkey | Roomkey API | Discovery | Discovery | Medium | — | — |  | 2026-06-30 | Feb 24 - Pulled from Backlog - please see Item 1 Dependency | —
Decisions & Actions Needed from Leadership
# | Vendor | Decision / Action Required | Why It Matters | Impact if Delayed | Owner Needed | Deadline
1 | Roomkey | Secure an enterprise-level sponsor from an active pipeline client to advance the Roomkey commerical partnership | Vendor progression is contingent ojn demonstrated brand demand; without a comitted enterprise client, partnership prioritizaiton will not move forward | Largest portfolio opportunity slips impacted forecasted revenue timing and marrket expansion | Business | 2026-03-01
Key Dependencies & Risks
Vendor | Dependency | Impact | Status | Expected Close | Decision Needed
No Current Risks / Dependencies
Customer Demand Signal — Backlog Highlights
PMS Vendor | Product | Requesting Brand(s) | Pipeline Properties | Est. ARR ($K) | Priority Rationale
Source: IN-Gauge Hospitality PMS Integration Methods • 22 active integrations (PMS, EDW, API) • 3 planned 2026 • Live since 2017

## Integration Maturity
Integration Maturity Scorecard
Each dimension scored 0–3 • Target = 13+ for Ready • Reflects current production capability
PMS Vendor | Product | Transaction Depth | Data Latency | Hotel Support | Scalability | Vendor Support | Total (/15) | Maturity % | Status
Opera OnPrem | Simphony OnPrem | 3 | 1 | 3 | 3 | 2 | 12 | 80% | Viable
Opera Cloud | OHIP API | 3 | 3 | 3 | 2 | 3 | 14 | 93.33% | Ready
FSPMS | FSPMS PMS | 3 | 1 | 2 | 2 | 2 | 10 | 66.67% | Viable
Lightspeed | Lightspeed PMS | 2 | 1 | 2 | 2 | 2 | 9 | 60% | Gaps
FOSSE | FOSSE PMS | 2 | 1 | 2 | 2 | 2 | 9 | 60% | Gaps
OnQ | OnQ PMS | 3 | 1 | 3 | 3 | 2 | 12 | 80% | Viable
Hyatt EDW | Hyatt EDW | 2 | 1 | 3 | 3 | 2 | 11 | 73.33% | Viable
InforHMS | Infor HMS | 2 | 1 | 2 | 2 | 2 | 9 | 60% | Gaps
Springer Miller | SMS | 2 | 1 | 1 | 1 | 1 | 6 | 40% | Gaps
Iberostar EDW | Iberostar EDW | 2 | 1 | 2 | 2 | 1 | 8 | 53.33% | Gaps
Prestige | Prestige PMS | 3 | 1 | 2 | 2 | 2 | 10 | 66.67% | Viable
StayNTouch | StayNTouch PMS | 2 | 1 | 2 | 2 | 2 | 9 | 60% | Gaps
EMMA TSA | TSA Extract | 2 | 1 | 2 | 2 | 2 | 9 | 60% | Gaps
Protel | Protel PMS | 2 | 1 | 2 | 1 | 2 | 8 | 53.33% | Gaps
HotelKey | HotelKey API | 3 | 3 | 2 | 2 | 3 | 13 | 86.67% | Ready
Cambridge TSA | TSA Extract | 2 | 1 | 2 | 2 | 2 | 9 | 60% | Gaps
NewHotel | NewHotel API | 2 | 3 | 1 | 1 | 2 | 9 | 60% | Gaps
TMS | TMS API | 2 | 3 | 1 | 1 | 2 | 9 | 60% | Gaps
RoomMaster | RoomMaster API | 2 | 3 | 1 | 1 | 1 | 8 | 53.33% | Gaps
VHP | VHP PMS | 2 | 1 | 2 | 2 | 1 | 8 | 53.33% | Gaps
Shiji SEP | Shiji SEP API | 2 | 3 | 2 | 2 | 3 | 12 | 80% | Viable
MEWS | MEWS API | 2 | 3 | 2 | 2 | 3 | 12 | 80% | Viable
Cloudbeds | Cloudbeds API | 3 | 3 | 2 | 2 | 2 | 12 | 80% | Planned — 2026
Hostaway | Hostaway API | 2 | 3 | 1 | 1 | 2 | 9 | 60% | Planned — 2026
Roomkey | Roomkey API | 3 | 3 | 2 | 3 | 2 | 13 | 86.67% | Planned — 2026

## Roadmap Timeline
Active Roadmap Timeline
Full delivery history 2017–2026 • Planned integrations with scheduled dates
PMS Vendor | Product | Hotel Brand(s) | Phase | Start | End | Duration (Days) | Status | Notes
Opera OnPrem | Simphony OnPrem | Multiple Brands | Production Ready | 2017-02-01 | 2017-02-22 | 21 | Complete | Signed off & handed over
Opera Cloud | OHIP API | Marriott / Hilton / Hyatt | Production Ready | 2021-01-15 | 2021-02-14 | 30 | Complete | Signed off & handed over
FSPMS | FSPMS PMS | Independent | Production Ready | 2018-01-15 | 2018-02-02 | 18 | Complete | Signed off & handed over
Lightspeed | Lightspeed PMS | Independent | Production Ready | 2018-04-01 | 2018-04-15 | 14 | Complete | Signed off & handed over
FOSSE | FOSSE PMS | Marriott | Production Ready | 2018-07-01 | 2018-07-15 | 14 | Complete | Signed off & handed over
OnQ | OnQ PMS | Hilton | Production Ready | 2017-04-01 | 2017-04-29 | 28 | Complete | Signed off & handed over
Hyatt EDW | Hyatt EDW | Hyatt | Production Ready | 2021-05-01 | 2021-05-29 | 28 | Complete | Signed off & handed over
InforHMS | Infor HMS | Multiple Brands | Certified | 2024-01-10 | 2024-01-31 | 21 | Complete | Signed off & handed over
Springer Miller | SMS | Independent / Luxury | Production Ready | 2019-01-10 | 2019-01-24 | 14 | Complete | Signed off & handed over
Iberostar EDW | Iberostar EDW | Iberostar | Certified | 2019-04-01 | 2019-04-19 | 18 | Complete | Signed off & handed over
Prestige | Prestige PMS | Prestige Portfolio | Production Ready | 2021-08-01 | 2021-08-22 | 21 | Complete | Signed off & handed over
StayNTouch | StayNTouch PMS | Independent / Lifestyle | Certified | 2024-04-01 | 2024-04-15 | 14 | Complete | Signed off & handed over
EMMA TSA | TSA Extract | TSA Portfolio | Production Ready | 2022-01-10 | 2022-01-28 | 18 | Complete | Signed off & handed over
Protel | Protel PMS | Independent | Production Ready | 2022-04-01 | 2022-04-22 | 21 | Complete | Signed off & handed over
HotelKey | HotelKey API | Multiple Brands | Production Ready | 2023-01-15 | 2023-02-12 | 28 | Complete | Signed off & handed over
Cambridge TSA | TSA Extract | Cambridge Portfolio | Production Ready | 2022-07-01 | 2022-07-19 | 18 | Complete | Signed off & handed over
NewHotel | NewHotel API | Independent | Production Ready | 2023-05-01 | 2023-05-15 | 14 | Complete | Signed off & handed over
TMS | TMS API | Independent | Production Ready | 2019-07-15 | 2019-08-02 | 18 | Complete | Signed off & handed over
RoomMaster | RoomMaster API | Independent | Production Ready | 2019-08-01 | 2019-08-15 | 14 | Complete | Signed off & handed over
VHP | VHP PMS | Independent | Production Ready | 2019-10-01 | 2019-10-15 | 14 | Complete | Signed off & handed over
Shiji SEP | Shiji SEP API | Shiji Portfolio | Certified | 2025-01-15 | 2025-02-05 | 21 | Complete | Signed off & handed over
MEWS | MEWS API | Boutique / Lifestyle | Certified | 2024-07-01 | 2024-07-22 | 21 | Complete | Signed off & handed over
Cloudbeds | Cloudbeds API | Multiple / TBD | Discovery | 2026-04-01 | 2026-06-30 |  | On Deck | Approve Cloudbeds as a Q2/Q3 build candidate contingent on commercial terms and a validated revenue case.
Hostaway | Hostaway API | Independent / Hybrid | Discovery | 2026-04-01 | 2026-06-30 |  | On Deck | Approve Hostaway as a Q2/Q3 build candidate contingent on commercial terms and a validated revenue case.
Roomkey | Roomkey API | IHG | Discovery | 2026-04-01 | 2026-06-30 |  | Discovery | We will not allocate engineering time on RoomKey until IHG demand is contractually real and access terms are clear.

## Capability Reference
Technical Capability Reference
Detailed per-vendor capability assessment • 22 active + 3 planned
PMS Vendor | Product | Auth Method | Data Direction | Real-Time | Historical Backfill | Upsells | Packages | Segments | Capability Score (/5)
Opera OnPrem | Simphony OnPrem | S3 SSE + Validation | Unidirectional | No | Yes | Yes | Yes | No | 3
Opera Cloud | OHIP API | Broker Token + S3 SSE | Bidirectional | Partial | Yes | Yes | Yes | Yes | 4.5
FSPMS | FSPMS PMS | S3 SSE | Unidirectional | No | Yes | Yes | Yes | No | 3
Lightspeed | Lightspeed PMS | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
FOSSE | FOSSE PMS | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
OnQ | OnQ PMS | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
Hyatt EDW | Hyatt EDW | PGP + S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
InforHMS | Infor HMS | S3 SSE | Unidirectional | No | Yes | Yes | Yes | No | 3
Springer Miller | SMS | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
Iberostar EDW | Iberostar EDW | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
Prestige | Prestige PMS | Token + SSE | Unidirectional | No | Yes | Yes | Yes | No | 3
StayNTouch | StayNTouch PMS | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
EMMA TSA | TSA Extract | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
Protel | Protel PMS | Token + SSE | Unidirectional | No | Yes | Yes | Yes | No | 3
HotelKey | HotelKey API | Token + SSE | Bidirectional | Yes | Yes | Yes | Yes | Yes | 5
Cambridge TSA | TSA Extract | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
NewHotel | NewHotel API | Token + SSE | Unidirectional | Yes | Yes | Yes | No | No | 3
TMS | TMS API | Token + SSE | Unidirectional | No | Yes | Yes | No | No | 2
RoomMaster | RoomMaster API | Token + SSE | Unidirectional | No | Yes | Yes | No | No | 2
VHP | VHP PMS | S3 SSE | Unidirectional | No | Yes | Yes | No | No | 2
Shiji SEP | Shiji SEP API | Token + SSE | Unidirectional | No | Yes | Yes | Yes | No | 3
MEWS | MEWS API | Token + SSE | Unidirectional | No | Yes | Yes | Yes | No | 3
Cloudbeds | Cloudbeds API | OAuth2 (TBD) | Bidirectional | Partial | Yes | Yes | Yes | No | Planned
Hostaway | Hostaway API | OAuth2 (TBD) | Unidirectional | No | Yes | Yes | No | No | Planned
Roomkey | Roomkey API | OAuth2 (TBD) | Bidirectional | Partial | Yes | Yes | Yes | No | Discovery

## Backlog
Backlog — Pending Discovery
Vendors not yet scheduled • Will enter roadmap planning once active integrations reach steady state
PMS Vendor | Product | Integration Model | API Maturity | Brand Interest | Pipeline Properties | Notes
Maestro PMS | Maestro | API + R&A (TBD) | Medium | Independent / Casino | 0 | Moderate technical feasibility but limited enterprise pull. Priority increases only if casino/independent portfolio expansion aligns with revenue targets. Currently low strategic urgency.
Clock PMS | Clock PMS+ | API | High | Requires Discovery | 0 | Technically mature and scalable integration model. Requires formal discovery to validate revenue concentration and overlap with target EU expansion strategy. High feasibility; demand validation pending.
Apaleo | Apaleo PMS | API | High | Requires Discovery | 0 | Technically attractive with strong developer-first model. Ideal for automation-heavy integrations. Strategic candidate for EU cloud expansion, contingent on confirmed brand/property pipeline.
WebRezPro | WebRezPro | API | Medium | Requires Discovery | 0 | Feasible but limited strategic lift. Prioritization tied directly to confirmed multi-property demand or competitive displacement opportunity.
RoomRaccoon | RoomRaccoon | API | Medium | Boutique / Independent | 0 | Emerging EU opportunity. Moderate technical effort. Prioritize if EU mid-market strategy accelerates or partner-led opportunity materializes.
Amadeus PMS | Amadeus Property | API | High | Marriott / Hilton | 0 | High strategic value. Direct enterprise brand alignment. Integration increases defensibility within Tier 1 accounts. Candidate for roadmap acceleration if revenue concentration supports allocation.
Cenium | Cenium PMS | API | Low | Requires Discovery | 0 | Low API maturity increases implementation complexity and cost. Prioritize only with contracted Nordic portfolio expansion. Otherwise defer.
Hapi | Hapi Hotel Hub | API (middleware) | Medium | Requires Discovery | 2 | Middleware reduces integration lift but introduces dependency risk. Validate scalability and data completeness before roadmap inclusion. Moderate opportunity pending validation.
Little Hotelier | Little Hotelier | API | Medium | Independent | 0 | Backed by established distribution network. Useful for independent penetration strategy. Requires confirmation of volume potential before prioritization.
ResNexus | ResNexus | API | Low | Requires Discovery | 0 | Lower maturity and unclear strategic lift. Remains backlog unless tied to material revenue opportunity.
10 additional PMS vendors tracked in this backlog • Prioritization subject to roadmap capacity and partnership agreements

## ARR Impact Tracker (hidden)
ARR Impact Tracker
Pipeline revenue by integration stage • Full platform history 2017–2026
Integration | Product | ARR Stage | Pre-2022 ARR ($K) | 2022–2023 ARR ($K) | 2024–2025 ARR ($K) | 2026 Pipeline ($K) | Status | Notes
Opera OnPrem | Simphony OnPrem | Live | 425 | - | - | - | Complete | 85 props. Flagship PMS since 2017.
OnQ | OnQ PMS | Live | 1050 | - | - | - | Complete | 210 props. Largest ARR. Hilton EDW.
FSPMS | FSPMS PMS | Live | 90 | - | - | - | Complete | 18 props. Stable since 2018.
Lightspeed | Lightspeed PMS | Live | 60 | - | - | - | Complete | 12 props. Stable since 2018.
FOSSE | FOSSE PMS | Live | 155 | - | - | - | Complete | 31 props. Marriott-aligned. Stable since 2018.
Springer Miller | SMS | Live | 40 | - | - | - | Complete | 8 props. Stable since 2019.
Iberostar EDW | Iberostar EDW | Live | 190 | - | - | - | Complete | 38 props. File delivery issue resolved.
TMS | TMS API | Live | 35 | - | - | - | Complete | 7 props. Stable since 2019.
RoomMaster | RoomMaster API | Live | 25 | - | - | - | Complete | 5 props. Stable since 2019.
VHP | VHP PMS | Live | 50 | - | - | - | Complete | 10 props. Stable since 2019.
Hyatt EDW | Hyatt EDW | Live | 475 | - | - | - | Complete | 95 props. PGP key rotation due Mar 31.
Opera Cloud | OHIP API | Live | 310 | - | - | - | Complete | 42 props. OHIP v2 migration required Q3 2026.
Prestige | Prestige PMS | Live | 85 | - | - | - | Complete | 15 props. Stable since 2021.
EMMA TSA | TSA Extract | Live | - | 125 | - | - | Complete | 25 props. Stable since 2022.
Protel | Protel PMS | Live | - | 45 | - | - | Complete | 9 props. Stable since 2022.
Cambridge TSA | TSA Extract | Live | - | 90 | - | - | Complete | 18 props. Stable since 2022.
HotelKey | HotelKey API | Live | - | 85 | - | - | Complete | 14 props. Bidirectional. Stable since 2023.
NewHotel | NewHotel API | Live | - | 30 | - | - | Complete | 6 props. Event-driven. Stable since 2023.
InforHMS | Infor HMS | Live | - | - | 135 | - | Complete | 22 props. Mapping issue resolved.
StayNTouch | StayNTouch PMS | Live | - | - | 55 | - | Complete | 11 props. Stable since 2024.
MEWS | MEWS API | Live | - | - | 125 | - | Complete | 19 props. 6 pipeline onboarding.
Shiji SEP | Shiji SEP API | Live | - | - | 100 | - | Complete | 16 props. Monitor Shiji 2.0 changes.
Cloudbeds | Cloudbeds API | Pipeline | - | - | - | 65 | On Deck | Q2 2026 target. Agreement not yet initiated.
Hostaway | Hostaway API | Pipeline | - | - | - | 40 | On Deck | Q2 2026 target. Agreement not yet initiated.
Roomkey | Roomkey API | Pipeline | - | - | - | 75 | On Deck | Q3 2026 target. IHG relationship required.
ARR Summary by Stage
Live ARR (Unlocked) |  |  | 3780
Pipeline ARR (Committed) |  |  | 180
At-Risk ARR (Blocked) |  |  | 0
Total Addressable (All) |  |  | 3960

## Partnership Status (hidden)
Partnership Status
Commercial agreement tracking • Separate from technical readiness • As of February 18, 2026
PMS Vendor | Product | Agreement Stage | Owner | Target Date | Days Until Deadline | Risk Level | Notes / Next Action
Opera OnPrem | Simphony OnPrem | Signed & Active | Andy Sena | 2017-02-22 | Signed Feb 2017 | Low | Agreement executed Feb 2017. Annual renewal. Signed off & fully operational.
OnQ | OnQ PMS | Signed & Active | Andy Sena | 2017-04-29 | Signed Apr 2017 | Low | Agreement executed Apr 2017. Hilton corporate. Annual EDW schema review Q2 2026.
FSPMS | FSPMS PMS | Signed & Active | Andy Sena | 2018-02-02 | Signed Feb 2018 | Low | Agreement executed Feb 2018. Standard SFTP renewal. Fully operational.
Lightspeed | Lightspeed PMS | Signed & Active | Andy Sena | 2018-04-15 | Signed Apr 2018 | Low | Agreement executed Apr 2018. Fully operational.
FOSSE | FOSSE PMS | Signed & Active | Andy Sena | 2018-07-15 | Signed Jul 2018 | Low | Agreement executed Jul 2018. Marriott-aligned. Fully operational.
Springer Miller | SMS | Signed & Active | Andy Sena | 2019-01-24 | Signed Jan 2019 | Low | Agreement executed Jan 2019. DBF format. Fully operational.
Iberostar EDW | Iberostar EDW | Signed & Active | Andy Sena | 2019-04-19 | Signed Apr 2019 | Low | Agreement executed Apr 2019. File delivery issue resolved. Fully operational.
TMS | TMS API | Signed & Active | Andy Sena | 2019-08-02 | Signed Aug 2019 | Low | Agreement executed Aug 2019. Fully operational.
RoomMaster | RoomMaster API | Signed & Active | Andy Sena | 2019-08-15 | Signed Aug 2019 | Low | Agreement executed Aug 2019. Fully operational.
VHP | VHP PMS | Signed & Active | Andy Sena | 2019-10-15 | Signed Oct 2019 | Low | Agreement executed Oct 2019. Fully operational.
Opera Cloud | OHIP API | Signed & Active | Andy Sena | 2021-02-14 | Signed Feb 2021 | Medium | Agreement executed Feb 2021. OHIP v2 migration required Q3 2026 — monitor Oracle comms.
Hyatt EDW | Hyatt EDW | Signed & Active | Andy Sena | 2021-05-29 | Signed May 2021 | High | Agreement executed May 2021. PGP key rotation due Mar 31 — coordinate with Hyatt IT.
Prestige | Prestige PMS | Signed & Active | Andy Sena | 2021-08-22 | Signed Aug 2021 | Low | Agreement executed Aug 2021. 11-file S3 model. Fully operational.
EMMA TSA | TSA Extract | Signed & Active | Andy Sena | 2022-01-28 | Signed Jan 2022 | Low | Agreement executed Jan 2022. TSA option codes. Fully operational.
Protel | Protel PMS | Signed & Active | Andy Sena | 2022-04-22 | Signed Apr 2022 | Low | Agreement executed Apr 2022. Token-secured API. Fully operational.
Cambridge TSA | TSA Extract | Signed & Active | Andy Sena | 2022-07-19 | Signed Jul 2022 | Low | Agreement executed Jul 2022. Fully operational.
HotelKey | HotelKey API | Signed & Active | Andy Sena | 2023-02-12 | Signed Feb 2023 | Low | Agreement executed Feb 2023. Bidirectional. High-value — prioritize renewal.
NewHotel | NewHotel API | Signed & Active | Andy Sena | 2023-05-15 | Signed May 2023 | Low | Agreement executed May 2023. Event-driven. Fully operational.
InforHMS | Infor HMS | Signed & Active | Andy Sena | 2024-01-31 | Signed Jan 2024 | Low | Agreement executed Jan 2024. Mapping issue resolved. Fully operational.
StayNTouch | StayNTouch PMS | Signed & Active | Andy Sena | 2024-04-15 | Signed Apr 2024 | Low | Agreement executed Apr 2024. Fully operational.
MEWS | MEWS API | Signed & Active | Andy Sena | 2024-07-22 | Signed Jul 2024 | Low | Agreement executed Jul 2024. 6 pipeline props onboarding. Fastest-growing boutique PMS.
Shiji SEP | Shiji SEP API | Signed & Active | Andy Sena | 2025-02-05 | Signed Feb 2025 | Medium | Agreement executed Feb 2025. Monitor Shiji 2.0 platform expansion.
Cloudbeds | Cloudbeds API | Not Started | TBD | 2026-03-31 | 35d | Medium | Q2 2026 target. Partnership agreement required before build can commence.
Hostaway | Hostaway API | Not Started | TBD | 2026-03-31 | 35d | Medium | Q2 2026 target. API-first — fast build once agreement signed.
Roomkey | Roomkey API | Not Started | TBD | 2026-04-30 | 65d | Medium | Q3 2026 target. IHG-backed. IHG commercial engagement required first.
Formulas:
Days Until Deadline = IF([Target Date]<TODAY(),"Overdue",INT([Target Date]-TODAY())&"d")