## Executive Summary
POS Integration Roadmap
Month-End Report • As of February 18, 2026
Active Integrations — Status at a Glance
POS Vendor | Product | Phase | Status | Risk | Live Props | Pipeline Props | Est. Pipeline ARR ($K) | Expected Close | Next Action
Oracle | Simphony | Production Ready | Complete | Low |  |  |  | Jun 30, 2025 | No Further Action - In Production & Ready for Onboarding
Toast (Ex+B37+A23:I2+A23:J24 | Toast POS | Production Ready | Complete | None |  |  |  | Jun 30, 2025 | No Further Action - In Production & Ready for Onboarding
Toast (API) | Toast POS | In Progress | In Progress | Medium |  |  |  | Mar 31, 2026 | API Medallion ETL underway
Oracle MICROS | Simphony / 3700 | Production Ready | Complete | None |  |  |  | Mar 31, 2026 | No Further Action - In Production & Ready for Onboarding
Shiji Infrasys | Infrasys POS | Certified | Complete | None |  |  |  | Sep 30, 2025 | No Further Action - In Production & Ready for Onboarding
Square | Square POS | Certified | Complete | None | 0 | 0 |  | Sep 30, 2025 | No Further Action - In Production & Ready for Onboarding
Agilysys | InfoGenesis POS | R&A Setup | In Progress | Medium | 0 |  |  | Mar 31, 2026 | Feb 24 - R&A analysis underway - Escalation to Business on Engagement
NCR Aloha | Aloha POS | Discovery | Discovery | Medium | 0 | 2 |  | Jun 30, 2026 | Feb 24 - Decision #2 Needs to be Addressed
Twinsoft | Twinsoft | Discovery | Discovery | Low | 0 | 16 |  | Apr 1, 2026 | Feb 24 - Antonis Arapoglou (Sani Ikos) engaged and actively looking to schedule time to technical validation & feasibility to see if we can meet April 1 Deadline
Clover | Clover POS | Discovery | Discovery | Low | 0 | 0 |  | Jun 30, 2026 | Feb 24 - Selected from Backlog, Business Account Created w/ Clover - Assessment underway. No current properties in Pipeline
Decisions & Actions Needed from Leadership
# | Vendor | Decision / Action Required | Why It Matters | Impact if Delayed | Owner Needed | Deadline
1 | Agilysys | Frank Abad (Hilton) has indicated that the engagement is currently on hold pending further review by Hilton’s VP of IT and additional discussions with Sponsor John P. I have requested the name of the VP of IT from Frank so we can align internally and support the appropriate outreach. We will need Business support to help re-enable engagement with both the Sponsor and Hilton leadership to move this initiative forward. | The engagement is not stalled at a technical level — it is paused at the VP of IT layer (Hilton). That means progression is now dependent on executive alignment, not delivery capability. Without engagement at that level, the initiative will not advance regardless of readiness on our side. | The core risk is not technical feasibility — it is executive momentum loss, which can translate into delay, reprioritization, or eventual disengagement. | Business/Partners | 2026-03-01
2 | NCR Aloha / Clover | Andy confirmed with Lee Lewin (NCR Voyix) that for integration with NCR Aloha under their Restricted Use Agreement (RUA) process, a virtual test environment is not currently available. As a result, NCR requires the purchase of a dedicated Aloha server and POS terminal to support development and testing for Certfication path | To move forward with the NCR Aloha testing environment through NCR Voyix, we would incur approximately $4,000 in one-time setup costs and $300 per month ongoing. This represents the required non-production environment investment to enable certification, testing, and integration support — not per-property deployment expense. We would need further approval based on Pipeline (2 Properties) to move forward at this time. | The primary risk is that we incur $4,000 upfront and $300/month ongoing without sufficient Aloha pipeline volume to justify the investment. If adoption is lower than expected, this becomes sunk enablement cost with limited ROI, and we remain dependent on NCR Voyix’s environment and process for ongoing support. | Business/Partners | 2026-03-01
3 | Toast POS | Jordan Moser (Toast) has mentioned they are looking to move forward with Partnership in 2026 given Marriott (Or other Sponsor) can be provided and drive engagement. Require Business support on Sponsors for potential Pipelines that can help drive partnership engagement. | Toast partnership progression in 2026 is contingent upon demonstrating sponsor-backed demand (e.g., Marriott or comparable enterprise account). Without visible pipeline support, partnership prioritization may stall. | If we cannot provide credible sponsor-backed opportunities, Toast may delay formal partnership alignment, limiting our ability to scale within their ecosystem and slowing enterprise F&B expansion. | Business/Partners | 2026-03-01
Key Dependencies & Risks
Vendor | Dependency | Impact | Status | Expected Close | Decision Needed
Agilysys | Engagement Delayed Pending Hilton Approval/Sponsorship | High | Delayed | TBD - Andy has followed up to confirm VP Name & Timeline | Determine primary sponsor strategy — proceed with Hilton engagement or designate an alternate enterprise client to drive vendor approval and partnership progression.
Customer Demand Signal — Backlog Highlights
POS Vendor | Product | Requesting Brand(s) | Pipeline Properties | Est. ARR ($K) | Priority Rationale
Xn Global Systems | xn | TBD | 6 | TBD | 6 pipeline properties already identified — highest demand in backlog
Twinsoft | Sani Ikos | TBD | 18 | TBD | Twinsoft supports a portfolio of 18 properties with highly seasonal demand profiles. Pipeline ARR is based on annualized per-property revenue, with peak-season activation materially accelerating value realization.
15 additional vendors tracked in the 'Backlog' tab. Full maturity scoring in 'Integration Maturity'. Technical specs in 'Capability Reference'.

## Integration Maturity
Integration Maturity Scorecard
Each dimension scored 0–3 • Target = 15 (maximum possible)
POS Vendor | Product | Transaction Depth | Data Latency | Hotel Support | Scalability | Vendor Support | Total (/15) | Maturity % | Status
Oracle | Simphony | 3 | 1 | 1 | 2 | 2 | 9 | 60% | Gaps
Toast | Toast POS | 3 | 3 | 2 | 3 | 3 | 14 | 93.33% | Ready
Oracle MICROS | Simphony / 3700 | 3 | 2 | 3 | 3 | 2 | 13 | 86.67% | Ready
Shiji Infrasys | Infrasys POS | 3 | 1 | 3 | 3 | 3 | 13 | 86.67% | Ready
NCR Aloha | Aloha POS | 3 | 2 | 2 | 3 | 3 | 13 | 86.67% | Ready
Maître'D | Maître'D POS | 1 | 1 | 2 | 2 | 2 | 8 | 53.33% | Gaps
Square | Square POS | 3 | 3 | 2 | 3 | 3 | 14 | 93.33% | Ready
Clover | Clover POS | 3 | 2 | 2 | 3 | 3 | 13 | 86.67% | Ready
Lightspeed | Lightspeed K-Series | 3 | 2 | 2 | 3 | 3 | 13 | 86.67% | Ready
Revel | Revel Systems POS | 3 | 2 | 2 | 3 | 3 | 13 | 86.67% | Ready
TouchBistro | TouchBistro POS | 1 | 1 | 2 | 2 | 2 | 8 | 53.33% | Gaps
Agilysys | InfoGenesis POS | 3 | 2 | 3 | 3 | 2 | 13 | 86.67% | Ready
PAR Brink | PAR Brink POS | 3 | 2 | 2 | 3 | 3 | 13 | 86.67% | Ready
Epos Now | Epos Now | 3 | 3 | 2 | 3 | 2 | 13 | 86.67% | Ready
Silverware | Silverware POS | 3 | 2 | 3 | 3 | 2 | 13 | 86.67% | Ready
SpeedLine | SpeedLine POS | 3 | 1 | 2 | 2 | 2 | 10 | 66.67% | Viable
Squirrel | Squirrel Cloud / 11 | 3 | 2 | 2 | 2 | 2 | 11 | 73.33% | Viable
SailPOS | SailPOS | 3 | 2 | 1 | 2 | 1 | 9 | 60% | Gaps
Focus | FocusPOS | 3 | 2 | 1 | 2 | 2 | 10 | 66.67% | Viable
Twinsoft | Twinsoft | 3 | 2 | 2 | 2 | 2 | 11 | 73.33% | Viable

## Roadmap Timeline
Active Roadmap Timeline
Showing only integrations with scheduled or completed work
POS Vendor | Product | Hotel Brand(s) | Phase | Start | End | Duration (Days) | Status | Notes
Toast | Toast POS | Marriott / Hilton / Independent | Extraction Build | 2025-02-01 | 2025-02-16 | 15 | Complete | Signed off & handed over
Square | Square POS | Marriott / Hilton / Hyatt / Independent | API Build | 2025-02-01 | 2025-02-16 | 15 | Complete | Signed off & handed over
Oracle | Simphony | Marriott / Hilton / Hyatt / Independent | Hybrid Build | 2025-03-01 | 2025-03-20 | 19 | Complete | Signed off & handed over
Shiji Infrasys | Infrasys POS | Hyatt | API Build | 2025-10-14 | 2025-11-01 | 18 | Complete | Signed off & handed over
Oracle MICROS | Simphony / 3700 | Independent / Hyatt / Marriott | API Build | 2026-01-15 | 2026-02-05 | 21 | Complete | Signed off & handed over
Toast | Toast POS | Marriott / Hilton / Independent | API Testing | 2026-02-01 | 2026-03-15 | 42 | In Progress | API Medallion ETL underway
Agilysys | InfoGenesis POS | Hilton | R&A Setup | 2026-02-12 | 2026-02-27 | 15 | In Progress | Reporting access granted — analysis underway
Twinsoft | Twinsoft | Sani Ikos | Discovery | 2026-02-27 | 2026-03-30 | 31 | In Progress | Client/Vendor Engagement
NCR | Aloha | Independent | Discovery | 2026-02-27 | 2026-04-30 | 62 | In Progress | Client/Vendor Engagement
Clover | Clover | TBD | Discovery | 2026-02-27 | 2026-06-30 | 123 | In Progress | Developer Portal Initiation

## Capability Reference
Technical Capability Reference
Detailed per-vendor capability assessment • Scored vendors only
POS Vendor | Product | Auth Method | Data Direction | Real-Time | Historical Backfill | Check-Level | Line Items | Modifiers | Capability Score (/5)
Oracle | Simphony | OIDC / Direct | Unidirectional | No | Yes | Yes | Yes | Yes | 4
Toast (Extraction) | Toast POS | OIDC / Direct | Unidirectional | No | Yes | Yes | Yes | Yes | 4
Toast (API) | Toast POS | OAuth2 | Bidirectional | Partial | Yes | Yes | Yes | Yes | 4.5
Oracle MICROS | Simphony / 3700 | OAuth2 | Bidirectional | Partial | Yes | Yes | Yes | Yes | 4.5
Shiji Infrasys | Infrasys POS | OAuth2 | Bidirectional | Partial | Yes | Yes | Yes | Yes | 4.5
Square | Square POS | OAuth2 | Bidirectional | Yes | Yes | Yes | Yes | Partial | 4.5
Clover | Clover POS | OAuth2 | Bidirectional | Yes | Yes | Yes | Yes | Partial | 4.5
Agilysys | InfoGenesis POS | OAuth2 | Bidirectional | Partial (Near Real Time/Event) | Yes | Yes | Yes | Yes | 4
Twinsoft | Twinsoft | OAuth2 | Bidirectional | Yes | Yes | Yes | Yes | Partial | 4.5

## Backlog
Backlog — Pending Discovery
Vendors not yet scheduled • Will enter pipeline based on customer demand and capacity
POS Vendor | Product | Integration Model | API Maturity | Brand Interest | Pipeline Properties | Notes
Maître'D | Maître'D POS | R&A / Extract (TBD) | Low | Requires Discovery | 1
Lightspeed | Lightspeed K-Series | API | High | Marriott | 0
Revel | Revel Systems POS | API | High | Requires Discovery | 0
TouchBistro | TouchBistro POS | Partner / Marketplace (TBD) | Medium | Requires Discovery | 0
PAR Brink | PAR Brink POS | API | High | Requires Discovery | 0
Epos Now | Epos Now | API | High | Requires Discovery | 0
Silverware | Silverware POS | API (licensed) + R&A | Medium | Requires Discovery | 1
SpeedLine | SpeedLine POS | File API / R&A (batch) | Medium | Requires Discovery | 0
Squirrel | Squirrel Cloud / 11 | REST API / SDK+SQL | Medium | Requires Discovery | 0
SailPOS | SailPOS | File API / R&A (batch) | Medium | Requires Discovery | 0
Focus | FocusPOS | API | Medium | Requires Discovery | 0
Zucchetti Group | TCPOS | API | Medium | Requires Discovery | 0
TBD | Emma | TBD | Low | Requires Discovery | 0
Xn Global Systems | xn | API | Medium | Requires Discovery | 6 | 6 pipeline properties
Zonal | Zonal | API | Low | Requires Discovery | 1

## ARR Impact Tracker (hidden)
ARR Impact Tracker
Pipeline revenue by integration stage • As of February 18, 2026
Integration | Product | ARR Stage | H1 2025 ($K) | H2 2025 ($K) | Q1 2026 ($K) | Q2 2026 ($K) | Status | Notes
Oracle Simphony | Simphony | Live | 180 | - | - | - | Complete | 25 live properties; fully ramped
Toast (Extraction) | Toast POS | Live | 35 | - | - | - | Complete | 5 live properties; fully ramped
Square | Square POS | Live | - | 50 | - | - | Complete | Signed off H2 2025; no active props
Shiji Infrasys | Infrasys POS | Live | - | 90 | - | - | Complete | 1 live, 10 pipeline ready to onboard
Oracle MICROS | Simphony / 3700 | Pipeline | - | - | 120 | - | Complete | 10 pipeline props; partnership pending
Toast (API) | Toast POS | Pipeline | - | - | 200 | - | In Progress | Testing phase; ETL build underway
Agilysys | InfoGenesis POS | At Risk | - | - | 300 | - | Blocked | Partnership blocked; no owner assigned
NCR Aloha | Aloha POS | Pipeline | - | - | - | 50 | On Deck | Awaiting roadmap approval
Twinsoft | Twinsoft | Pipeline | - | - | - | 100 | On Deck | 18 pipeline props; Sani Ikos brand
Clover | Clover POS | Pipeline | - | - | - | 50 | On Deck | Awaiting roadmap approval
ARR Summary by Stage
Live ARR (Unlocked) |  |  | 355
Pipeline ARR (Committed) |  |  | 520
At-Risk ARR (Blocked) |  |  | 300
Total Addressable (All) |  |  | 1175

## Partnership Status (hidden)
Partnership Status
Commercial agreement tracking • Separate from technical readiness
POS Vendor | Product | Agreement Stage | Owner | Target Date | Days Until Deadline | Risk Level | Notes / Next Action
Oracle Simphony | Simphony | Signed & Active | Andy Sena | Jun 30, 2025 | — | Low | Agreement executed; fully operational. Annual renewal due Jun 2026.
Toast (Extraction) | Toast POS | Signed & Active | Andy Sena | Jun 30, 2025 | — | Low | Extraction agreement active. API agreement separate — see row below.
Square | Square POS | Signed & Active | Andy Sena | Sep 30, 2025 | — | Low | Agreement executed; fully operational.
Shiji Infrasys | Infrasys POS | Signed & Active | Andy Sena | Sep 30, 2025 | — | Low | Agreement executed. 10 pipeline props ready; onboarding can proceed.
Oracle MICROS | Simphony / 3700 | Signed & Active | Andy Sena | Feb 28, 2026 | ~10d | High | Integration complete; commercial terms drafted. Signature required to unblock 10 pipeline props.
Toast (API) | Toast POS | Pending Signature | Andy Sena | Feb 28, 2026 | ~10d | High | API testing underway without formalized agreement. Must close before production access.
Agilysys | InfoGenesis POS | No Owner / Blocked | TBD | Not Set | — | Critical | No internal owner assigned. No vendor engagement initiated. Blocks Hilton pipeline entirely.
NCR Aloha | Aloha POS | Not Started | TBD | Mar 31, 2026 | ~41d | Medium | Awaiting roadmap approval before initiating vendor outreach.
Twinsoft | Twinsoft | Not Started | TBD | Mar 30, 2026 | ~41d | Medium | 18 pipeline properties; Sani Ikos. Outreach not yet initiated.
Clover | Clover POS | Not Started | TBD | Jun 30, 2026 | ~132d | Low | Awaiting roadmap approval. Low urgency vs. other pipeline items.